## Dashboard Overview
Project Name | Status | Progress % | Budget | Actual Spend | Variance | Risk Level | Owner
CRM Upgrade | Green | 85% | 50000 | 46000 | 4000 | Low | Divya
Reporting Automation | Amber | 65% | 30000 | 28000 | 2000 | Medium | Divya
Process Improvement | Red | 40% | 20000 | 21000 | -1000 | High | Divya

## KPI Tracking
KPI | Target | Actual | Status | Comments
On-Time Delivery | 90% | 86% | Amber | Slight milestone delay
Budget Control | <10% variance | 8% variance | Green | Within acceptable range
Reporting Accuracy | 95% | 96% | Green | Above target
Stakeholder Updates Sent On Time | 100% | 100% | Green | All updates completed
Risk Resolution Rate | 85% | 78% | Amber | More follow-up needed

## Milestone Tracker
Milestone | Due Date | Status | Owner | Notes
Planning Complete | 2026-04-01 | Done | Divya | Completed on time
Dashboard Setup | 2026-04-05 | Done | Divya | Initial version ready
Stakeholder Review | 2026-04-10 | In Progress | Divya | Awaiting feedback
Final Sign-off | 2026-04-15 | Pending | Divya | Not started