## Raid Log
ID | Type | Description | Impact | Probability | Owner | Status | Mitigation
1 | Risk | Delay in stakeholder approval | High | Medium | PM | Open | Escalate early and follow up
2 | Issue | Resource shortage | Medium | High | Team Lead | In Progress | Reallocate resources
3 | Assumption | Vendor availability | Low | Low | PM | Confirmed | Monitor regularly
4 | Dependency | External API delivery | High | Medium | Tech Team | Pending | Track with vendor